My part: testing before a phase closes

The team builds a phase. Before the next one starts, I check the build against the requirement doc — feature by feature. If something is missing or not working, it goes back. When it's clean, I approve it and the next phase can begin.

Nandini  ·  Testing & Approval

Order of work

| Step | Who does it |
| --- | --- |
| 1. Requirement doc is final | Planning |
| 2. Phase is developed | Dev team |
| 3. Build is tested | Me |
| 4. Reported issues are fixed | Dev team |
| 5. Fixes are re-checked | Me |
| 6. Next phase starts | Dev team |

What I check

- Is every feature written in the doc actually there, and working the way it says?

- What happens when a user does something wrong — empty cart, wrong OTP, no internet, back button mid-payment?

- Is the data correct — order, subscription, address and wallet saved and shown properly?

- Did the new work break something that was already working?

- Anything that can be made easier for the user — I note it down, but it doesn't stop the phase.

How much time I need

| Phase | My testing | With one fix round |
| --- | --- | --- |
| Small change, 1–2 screens | 3–4 days | 5–6 days |
| One full module — login, catalog, orders | 4–5 days | 6–8 days |
| Payments, subscriptions, admin panel | 6 days | 8–10 days |

The first round of testing takes most of these days. Then I share the bug list, the team fixes it (usually 1–3 days — that is their time, not mine), and I re-check the fixes in about a day. Before release, the whole app needs 3 more days end to end.

What I need on day one

A working build with a version number, the final requirement doc for that phase, test login IDs, test payment and OTP details, and a list of what is included in this phase. If something is missing, I can't start — and those days don't count as testing days.

When I approve

Nothing broken, nothing working differently from the doc, and small issues either fixed or agreed to leave for later. One request: please don't push new code while a round of testing is running — I have to start that round again from zero.

These day counts are estimates. If a phase turns out bigger than what was handed over, I'll tell you the revised time on the first day itself.